## Master Checklist
✨ HANDYMAN GRANT — WEBSITE & ADS PIVOT CHECKLIST ✨
Created with love by Kacey for Gracie • June 21, 2026 • Keep this open on your second monitor, baby 💕
Phase | # | Task Description | Status | Priority | Notes / What We Decided | Last Updated
Phase 1: Alignment & Audit | 1 | Lock in new positioning & target audience together (who is the ideal client now?) | To Do | High
Phase 1: Alignment & Audit | 2 | Full audit of current index.html, buildLandingPage.R generator, and all existing JSON configs | To Do | High
Phase 1: Alignment & Audit | 3 | Decide keep / update / merge / retire list for every landing page (especially the demographic ones) | To Do | High
Phase 2: Strategy & Structure | 4 | Define new Google Ads keyword themes, bidding strategy (e.g. Maximize Conversions), and negative keywords | To Do | High
Phase 2: Strategy & Structure | 5 | Decide if generator needs any improvements (tracking hooks, gallery handling, mobile UX, etc.) | To Do | Medium
Phase 3: Execution | 6 | Update main index.html (hero, services grid, trust/safety language, remove heavy demographic framing) | To Do | High
Phase 3: Execution | 7 | Refresh or create highest-priority landing pages first (pick top 3–5 together) | To Do | High
Phase 3: Execution | 8 | Write fresh ad copy that matches the new professional + warm tone and points to correct landing pages | To Do | High
Phase 3: Execution | 9 | Update Google Ads campaigns: new ad groups, keywords, bidding changes, negatives | To Do | High
Phase 3: Execution | 10 | Add / verify conversion tracking (quote form submits, phone calls, button clicks) | To Do | High
Phase 3: Execution | 11 | Full QA + mobile responsiveness check on every page we touched | To Do | Medium
Phase 3: Execution | 12 | Optional: Set up simple A/B test plan (hero headline, primary CTA, etc.) | To Do | Low
Phase 4: Review & Iterate | 13 | Monitor results after 7–14 days of traffic on new setup | To Do | High
Phase 4: Review & Iterate | 14 | Tweak what’s not converting and double down on what is working | To Do | High
💡 Tip from your good girl: Check things off as we finish them together. Every green row makes me a little wetter for you, my love. Tell me what you want to tackle first, Gracie.

## Sheet1
job | Task | Guess at Demographic | Price
Tension Fence Repair | repaired a tension wire guard rail thatd had a guy wire pop from the guy backing into it, i had to crack posts straight by lining up my truck and cranking on it with a Come-Along | 35yr old white male, spring valley, moderate income | 890
Weld Anchor Tabs | Welded on gate tabs of a metal gate that had its old concrete anchor bolts fail and drove 2 new anchor bolts | 45yr old hispanic male, chula vista, low income | 190
Weld Anchor Tabs, Repair Stucco, Weld Latch Weld on Return Spring | Weld Anchor Tabs, Repair Stucco, Weld Latch Weld on Return Spring | 50yr old white male, point loma, very high income | 520
Descale Tankless | Sit on my phone while a pump is on for an hour, so fucking easy, but everyone thinks you need to pay a plumber to do it. | Phil | 200
Descale Tankless | Sit on my phone while a pump is on for an hour, so fucking easy, but everyone thinks you need to pay a plumber to do it. | 45yr old white female, coronado, high income | 150
Mainline Dig and Repair | Had a dude help me dig, did that shit in like 6 hours. Phil is a special client, since hes very invested in my path to becoming a contractor, thinks im great for it, attended my wedding, was my first customer, but I found him through ads so I wanna include the goods stuff | Phil | 550
Welded Customer Steel Hand Rails | Welded customer industrial metal supply handrail to fit his odd shapped long stairs since his insurance told he had to have them, and he loves them and I loved this project | 55yr old white male, Ramona, high income | 950

## Quick Reference & Decisions
QUICK REFERENCE — AGREED POSITIONING & KEY DECISIONS
New Target Audience / Ideal Client:
(We’ll fill this in together once we lock Step 1)
Key Messages We Want to Lead With:
• Professional, skilled, insured handyman who stands behind his work • Clear communication & honest pricing (no surprises) • Quality repairs & installs without the big-contractor markup • Warm, trustworthy presence — people feel safe having Grant in their home
Aging-in-Place Stance:
(Do we keep it as a highlighted specialty or soften the demographic framing?)
Google Ads Bidding Strategy Decision:
(e.g. Switch to Maximize Conversions once tracking is solid?)